## Project Plan and Gantt
Project Name | Personal Project - UFC:NOW
Project Manager | Alex Thain.
Project Deliverable
Scope Statement:
Start Date | 2019-01-02
End Date | 2019-01-28
Overall Progress | 85%
Tasks | Responsible | Start | End | Days | Status
Briefing on Personal Project | Alex T | 2019-01-02 | 2019-01-03 | 1 | Complete
Define Objectives | Alex T | 2019-01-03 | 2019-01-04 | 1 | Complete
Outline Reqs. | Alex T | 2019-01-07 | 2019-01-12 | 5 | Complete
Software Reqs. | Alex T | 2019-01-09 | 2019-01-11 | 2 | Complete
Develop SQL Database | Alex T | 2019-01-11 | 2019-01-15 | 4 | Complete
Develop Back-End Function | Alex T | 2019-01-17 | 2019-01-18 | 1 | Complete
Connect DB to Back-End App | Alex T | 2019-01-18 | 2019-01-19 | 1 | Complete
Testing | Alex T | 2019-01-18 | 2019-01-19 | 1 | In progress
Dev. Complete | Alex T | 2019-01-19 | 2019-01-20 | 1 | In progress
Develop Front-End | Alex T | 2019-01-20 | 2019-01-25 | 5 | In progress
Write Necessary JavaScript | Alex T | 2019-01-20 | 2019-01-25 | 5 | In progress
Write Necessary CSS | Alex T | 2019-01-20 | 2019-01-25 | 5 | In progress
Write Necessary HTML | Alex T | 2019-01-20 | 2019-01-25 | 5 | In progress
Hardware Config for Presentation | Alex T | 2019-01-26 | 2019-01-27 | 1 | Not started
Peer Review | Jim | 2019-01-26 | 2019-01-27 | 1 | Not started
Testing | Alex T | 2019-01-27 | 2019-01-28 | 1 | Not started
Launch |  | 2019-02-01 | 2019-02-02 | 1

## Stakeholder List
Stakeholder List
Name | Position | Role in project | Email address | Requirements | Expectations
John Smith | VP of Product | Final approval of milestones | john@123.com | Downtime of no longer than 20 minutes | QA to take less than 1 week, marketing to promote new features in newsletter

## Cost Baseline
Cost Baseline
Item/task | % Complete | Base Cost | Cost | Actual Cost | % Budget Spent
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
Communication Plan
Communication Type | Deliverable | Description | Delivery Method | Frequency | Owner | Audience
Presentation | 15-minute Powerpoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team