## Sheet1
ID | Theme | As a/an | I want to.. | So that.. | Notes | Priority | Status
1 | Web Site | User | Be able to view the latest event on the homepage. | I can catch up on what I've missed. | Pop-up video when user presses play. | Medium | Done
2 | Web Site | User | Be able to view the three best events of the past year. | I can see the best highlights. | Pop-up videos when user presses play. | Medium | Done
3 | Web Site | User | Be able to view the three latest events. | I can catch up on what I've missed. | Pop-up videos when user presses play. | Medium | Done
4 | Web Site | User | Be able to search for a fighter by name. | I can see info about my favourite fighter. | Dynamic search bar utilising the onInput function HTML/ JS. | High | Done
5 | Web Site | User | Be able to search for a fighter by weight class. | I can see everybody in a certain class. | Explore buttons for each weight class to refine display to show just those class fighters. | High | Done
6 | Web Site | User | Be able to search for a product by name. | I can buy my favourite items. | Dynamic search bar utilising the onInput function HTML/ JS. | High | Done
7 | Web Site | User | Be able to add a desired product to my basket. | I can proceed with ordering these items. | Desired feature but not sure if it will get completed in time. Maybe for version 1.2 | Medium | Not Complete
8 | Web Site | User | Be able to login. | I can see if about my account/ orders | Extra Bonus Feature. | Low | Not Complete
Product Backlog - User Stories